## Slide 1
P.M. PLAN
Notes: This your master slide. To fill, Copy and Paste a screenshot from slide 2. Slide 2 has the boxes that you can populate and change. See slide 2 for a description on what to fill each box with.
  *Note: P.M. Plan= Project Management Plan

## Slide 2
Purpose Provide affordable, accessible, and fun advocacy solutions for low-income communities in order to resolve the local substance abuse crisis. | Phase 1 (Planning): Site selection: Manila, Philippines & Virtual (Zoom) Phase 2 (Execution): 1. Virtual workshop via Zoom; 2. In-person training when social distance measures are eased (OCT) Phase 3 (Secure funding): Homemade materials will lower costs, GoFundMe & donations Phase 4 (Outreach): Conduct community outreach, recruit applicants, acquire new trainers, parental approval. Intent is to have the community build their own tables and programs. Phase 5 (Sustainability): Train the trainers, enable youth to train other youth, share successes in order to secure donations Minimum Requirements: Cost: 1,000PHP ($20) 1x Trainer for 25 kids Transportation= 1x Van, Bus, or 2x Cars  None for Virtual Event 1 x table (homemade): 1x tabletop, 4x legs, 1x net 2x bats (i.e. paddles) 1x ball (3 ideal) | Coordinating Instructions: Decision Point (DP) 1: Site Selection DP 2 (Funding): Self-Funding, GP Donation, Volunteers Minimum Viable Product= 1x complete tennis set with 3x kids Cost Assessment- Initial costs, 3-month, 6-month, 1-year, Long Term Legal Assessment Outreach: Social media and organic Recruitment: SMEs, table tennis enthusiasts, volunteers, ID at-risk communities
Situation The global pandemic has exacerbated preexisting systemic economic issues that will continue to devastate low-income communities in the Philippines and abroad. As a result, at-risk youth are at a greater risk of substance, sexual, and domestic abuse. With violence and displacement expected to increase, table tennis provides a low cost and affordable outreach solution that every person can play, at any age (there is no barrier to entry). Coupled with life skills coaching, at-risk youth will be provided an outlet for escaping abusive situations. |  | 
Why Table Tennis? Accessible to all: No arms, no problem You are in Control All Ages: 3-103 years old Easy to Make Simple and Fun Scholarship Opportunities: Skilled players can join leagues and compete for rewards |  | POCs & More Information: Arni Estacio (Certified PTTF/ITTF L1 -Coach Administrator): arniestacio@gmail.com Christopher Andrade (GP Founder): grassrootpeacebuilders@gmail.com More Information: https://ittffoundation.org/programmes/tt-dream-building/ongoing-projects/ slum-ping-pong-
Course of Action
Operation Table Tennis Warriors
12SEP2020
Timeline of Events:
03-10SEP20: Phase 1 Planning and site selection (Virtual)
11SEP20: Rehearsals
12SEP20: Conduct Virtual Event
  1300-1600- Event
  1700: After Action Review (AAR)
TBD: Next Event
ADD HASTAG
Homemade Table
No Hands, No Problem. Everyone Can Play!
Notes: Your 1-page Action Plan This chart forces you to focus your vision, articulate it on paper, and create an operational timeline centered around accomplishing your minimum viable product.
Starting from top to bottom going left to right fill in each box with the following items:
Title your project/business plan and put the start/end date
Photos Select emotionally charged photos that illustrate your mission, vision, and purpose.
Purpose= Mission statement Include the 5 w’s
  Who
  What
  When
  Where
  Why
Situation= This is your expanded “why” and quick overview of how you will accomplish your objective.
Why/Benefits?? This is a box to illustrate your unique value proposition  Call it whatever you want.
Course of Action= Detail your operation by phase. Include critical decision points or tasks that must be accomplished during each phase. Make this time based (this will reflect your “timeline of events” box)
Minimum Requirements= What do you need to make this operation work, think bare minimums required for social/ business proof of concept.
Coordinating Instructions=
  Decision Points= What decisions are critical to operational success
  Additional Considerations vital to the planning and execution of this operation
Point of Contact(s) (POC) & more information
Timeline of Events= Execution timeline by phase

## Slide 3
Notes: Place your PM Plan photos here as needed
***Want Guided Support?
This starter kit is designed for self-directed replication.
Pro members get access to guided build walkthroughs, editable template libraries, and AI companions to support real-world execution.
Learn more at peacebuilderacademy.com/pricing ***