## Requirements- MCDA
Requirement | Difficulty | Cost | Resources | Risk | Value | Skill Level | Total Score
Requirement X | 3 | 2 | 3 | 3 | 3 | 2 | 16
Requirement Y | 3 | 1 | 3 | 3 | 3 | 3 | 16
Requirement Z | 1 | 3 | 2 | 2 | 2 | 2 | 12
Ranking
Requirement A | Hard | 200 | 3 | High | High | Medium | 3
Requirement B | Medium | 100 | 3 | Medium | Med | High | 2
Requirement C | Easy | 300 | 2 | Low | Low | Medium | 1
Criteria Options | Examples | Classification
Ranking | 1-5/A-Z | Need
Scoring | 1-5/A-Z | Want
Specific #s | $/ 1234 | Expecation
Categories | L/M/H
Hybrid | $100 (H)

## Scope Statement
Project Objective | Description | Acceptance Criteria | Key Deliverabls | Scope Exclusions | Time & Cost Estimate | Constraints | Assumptions | Task ID #
Build member list | 30 people needed | Project manager verifies list | Member List | Paying members only | 4 hours * $10/hour= $40 | 1 admin person | Admin person available | A001

## Scope- Simple
In Scope |  |  | Out of scope
Category | Name | Description | Name | Description
Application | Module 1 |  | Module 3
Module 2
Features | Feature 1 |  | Feature 4
Feature 2
Feature 3
Processes | Process 1 | step 3-10
| Process 2 | steps 1-5
Documents | Supplier contract
Dependencies | Regulatory requirement nr 1/2021

## Schedule
|  |  | Initiating |  | Planning |  | Executing | [5 empty] | Closing
Action | Responsible | Contributor | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Milestone: Define business requirements | Project manager | Stakeholders | bar: Initiating Week 1
Execute project management plan | Project manager | Stakeholders
Milestone: PMP is approved | bar: Planning Week 3
Inform stakeholders of the start of the project
Validate requirements
Generate solutions
Write specifications
Validate specifications
Develop solution
Test solution
Go-live | bar: Executing Week 10

## Workbreakdown structure (hidden)
Work Breakdown Structure Table
Provide basic information about the project including: Project Title – The proper name used to identify this project; Project Reference / ID - The unique reference or ID for the project; Project Manager - the person with responsibility for the successful delivery of the project to time cost and quality. Project Sponsor - the person ultimately accountable for the success of the project. Prepared by – The person(s) preparing this document; Date/Control Number – The date the plan is finalized and the change or configuration item control number assigned.
Project Title: |  |  | Project Reference / ID:
Project Manager: |  |  | Project Sponsor:
Prepared by: |  |  | Date / Control Number:
Element Number | WBS Elements Activity, Task, or Sub-Task Name | Definition of Activity or Task (Description) | Responsible Person or Group | Estimated (E) or Actual (A) Cost (Cross reference to budget) | Project Phase (Cross reference to schedule)
The unique reference ID for the activity or task. | Enter the name or title of the Task, Sub-task, Activity or Deliverable. | Provide a brief description of this Activity, Task or Sub-Task. | Enter the person or group who are responsible | Enter the estimate or actual cost of the activity or task or add a cross reference to the budget. | Provide the name or number of the Project phase that this activity falls into.

## Milestone Chart
Milestone ID | Activity ID | Name | Events Triggered | Expected Date

## WBS
Project Name
Project Manager
Date
WORK BREAKDOWN STRUCTURE TEMPLATE - TASKS
Phase | Task No. | Description | Owner | Dependency | Resources Needed | Status | Cost | Start Date | Finish Date | Comments
Initiation | 1.1 | Task
Initiation | 1.1.1 | Subtask
Initiation | 1.1.2 | Subtask
Initiation | 1.1.3 | Subtask
Planning | 2.1 | Task
Planning | 2.1.1 | Subtask
Planning | 2.1.2 | Subtask
Planning | 2.1.3 | Subtask
Planning | 2.2 | Task
Planning | 2.2.1 | Subtask
Planning | 2.2.2 | Subtask
Planning | 2.2.3 | Subtask
Execution | 3.1 | Task
Execution | 3.1.1 | Subtask
Execution | 3.1.2 | Subtask
Execution | 3.1.3 | Subtask
Control | 4.1 | Task
Control | 4.1.1 | Subtask
Control | 4.1.2 | Subtask
Control | 4.1.3 | Subtask
Close | 5.1 | Task
Close | 5.1.1 | Subtask
Close | 5.1.2 | Subtask
Close | 5.1.3 | Subtask

## Risks
Risk Category | Description | Probability of appearance | Impact if the risk occurs | Quantification | Mitigation plan (i.e actions to reduce the likelihood of the risk happening) | Contingency plan (i.e actions if the risk occurs) | Owner | Progress | Status
Organizational | Personnel- Family Emergency | 10% | Schedule: 3 day delay | 3 days * 8 hours= 24 hours * $20/hour = -$480 | Weekly health and welfare check-ins to anticipate issues | 1. Offer team overtime 2. Contingency reserves--> Call freelancer | J. Smith (PM) | Ongoing

## Benefits
Activity | Benefit | Strategy Allignment | Timeframe | Owner | Metrics | Assumptions | Risks | Progress

## Costs
Approved Total Budget | 25000 | RON/EUR
Encountered costs | 10200 | RON/EUR
Remaining budget | 14800 | RON/EUR
DETAILS
Item | Approved Cost | Encountered Cost | Date | Comment
Purchase application | 10000
Purchase application |  | 5000 | 2011-01-01 | initial payment
Purchase application |  | 5000 | 2011-12-12 | final payment
Media | 1000 | 200 | 2011-03-02 | Google ads

## Resource allocation
For the weekly effort, please input the effort in HOURS
Summary
Number of resources |  | 3
Total budgeted MDs |  | 18.8
Total consumed MDs |  | 18.1333
|  |  |  | Initiating |  |  |  | Planning |  |  |  | Executing | [11 empty] | Closing
|  |  |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | Week 9 |  | Week 10 |  | Week 9 |  | Week 10
Resource name | Department | Total budgeted | Total consumed | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual | Budget | Actual
x | Compliance | 141 | 136 | 5 | 0 | 0 | 0 | 5 | 6 | 5 | 5 | 10 | 15 | 5 | 0 | 20 | 10 | 40 | 40 | 20 | 20 | 20 | 30 | 10 | 5 | 1 | 5
y | Sales
z
|  |  |  | 5 | 0 | 0 | 0 | 5 | 6 | 5 | 5 | 10 | 15 | 5 | 0 | 20 | 10 | 40 | 40 | 20 | 20 | 20 | 30 | 10 | 5 | 1 | 5

## Stakeholder Register
ID | Name | Contact Info | Role Title | Location | Expectations | Influence (L/M/H) | Internal/External | SH Engagement | Preferred Communication Method | Frequency
A001 | Joe Smith | joesmith@gmail.com | Angel Investor | Los Angeles/Virtual | Information, Funding, Expertise | H | Internal | Supportive | Phone Call | Bi-monthly
A002 | Brian Holder | bholder@gmail.com | CEO | London | Project Management, Mission, Vision | H | Internal | Leading | In-person | Daily
[8 empty] | Engagment Options | Communication Methods | Frequency
[8 empty] | Leading | Phone | Hourly
[8 empty] | Supportive | Text/Messaging App | Daily
[8 empty] | Neutral | In-person | Weekly
[8 empty] | Resistant | Email | Monthly
[8 empty] | Unaware | Presentation | Quarterly